| DRAFT ONLY ------------------- IDP Movement to Camps ------------------- CHECKLIST |  |
| --- | --- |
| BEFORE DEPARTING This checklist is for the monitoring of relocation of internally displaced persons camps or other sites. |  |
| Sector/Areas of Intervention | Standards and activities (Prior to and during the movement) |
| Protection | - Information about selection criteria and process had been shared to all IDPs - Consultation of beneficiaries through focus groups with different age, gender and background on all matters concerning the relocation process and management of the sites. - Consultation of members of the host community of different age, gender and background on all matters concerning the arrival of the beneficiaries and management of the sites. - Discussion about voluntariness prior to the movement - Coordination with all appropriate government, agencies, partners and police with female police presence on site during the movement - Allocation of units considered vulnerability of beneficiaries |
| Child Protection | - No unwanted separation of families, leading to separated or unaccompanied minors |
| GBV | - Lights (either connection to electricity or solar lanterns) - Locks for doors of toilets, bathing facilities and individual units |
| CCCM | - Land tenure status: whether public or private land, Government issued a document attesting to the allocation of the land for the purpose of the settlement - Go & see visits, ensuring an adequate representation of the population in terms of their age, gender and other aspects of diversity - Advance notification to beneficiaries about date, time and departure point for relocation (preferably 5-7 days in advance) - Adequate transport for beneficiaries and belongings, with adequate consideration of persons with specific needs (e.g. persons with disabilities, pregnant women, elderly) - Consultation and dissemination of house rules |
| WASH | - Gender-segregated toilets (unless community preference is for toilets shared by family) - Accessibility of toilets and bathing facilities to persons with disabilities - Onsite access to safe and reliable water supply (preference for direct connection to L2/L3 system with payment commitment in place) - Drainage system in place |
| Shelter | - Completion of proper shelter construction (walling, roofing, flooring) - Covered space is 3,5m2 by person, 18 m2 by family up to 5 persons - For ventilation, Min1m2 opening in two walls of the structure, Min 1/2m2 ventilation to all rooms - Min floor to ceiling height at walls of 2.1m (7ft) - The design should allow addition of at least one internal division to ensure privacy - Should be securable to ensure personal safety and safety of goods - Allow for access by persons with reduced mobility - Availability of safe cooking facilities at the site |
| Health | - Access to health facilities |
| Livelihood | - Access of livelihood from the site |

| RELOCATION CHECKLIST |  |
| --- | --- |
| UPON ARRIVAL The checklist is for the monitoring of relocation of internally displaced persons upon arrival in camps or at other sites. |  |
| Sector/Areas of Intervention | Standards and activities |
| Protection | - Assistance for specific needs (old care, disabilities, separated children, etc.) - Neighborhood Watch Committees, including female members |
| Child Protection | - Existence of Child Friendly Spaces - No unwanted separation of families, leading to separated or unaccompanied minors |
| GBV | - Existence of Women Friendly Spaces |
| CCCM | - Age and gender segregated camp management committees |
| WASH | - Sufficient supply of good quality drinking water to all beneficiaries - Proper solid waste disposal at the site |
| Shelter | - Access to appropriate space, depending on family size and indicators defined in prior step |
| Health | - Health and psychosocial services provided at the site - Health referral system established at the site |
| Education | - Existence of schools at or near nearby the camps – school name and distance from the relocation site(s) to be provided - Existence of nearby day care centers and distance from the relocation site - Knowledge on the new school and day care center |
| Livelihood | - Permission to work not required |